## Sheet1
Detailed working estimate for repair of Pump house and H.S.R of operation and maintenance for rural water scheme ramzan lassi goth taluka shah mureed district malir karachi
1 | Dismentiling cemennt concrete reinforced separating reinforce concrete from concrete cleaning and straightening the same (C.S.Item No. 20 Page No. 10)
H.S.R
| Top Slab |  |  | 1 | x | 11.5 | x | 11.5 | x | 0.5 | = | 66.125 | Cft
| Walls | 2 | x( | 11.5 | + | 10.25 | ) x | 1 | x | 4 | = | 174 | Cft
| Bottom Slab |  |  |  |  | 14.5 | x | 14.5 | x | 0.5 | = | 105.125 | Cft
| Beam | 2 | x ( | 11.5 | + | 10.25 | ) x | 1 | x | 1 | = | 43.5 | Cft
[10 empty] | Total | = | 388.75 | Cft
| Qty | 389 |  | Cft. | @ | Rs. | 5445 |  | P. % cft |  |  |  | Rs. | 21181.05
2 | Removing cement or lime plaster (C.S.Item No.53 Page No.13)
Pump House
| Inner | 2 | x ( | 10.25 | + | 10.25 | ) x | 11 |  |  | = | 451 | Sft.
| Outer | 2 | x ( | 11.5 | + | 11.5 | ) x | 11 |  |  | = | 506 | Sft.
[10 empty] | Total | = | 957 | Sft.
Deduction Door & Window
|  |  |  | Door |  | 2 | x | 3.5 | x | 6.5 | = | 45.5
|  |  |  | Window |  | 4 | x | 3 | x | 3 | = | 36
[10 empty] | Total | = | 81.5
[9 empty] | G.Total |  | = | 875.5
| Qty | 875.5 |  | Sft. | @ | Rs. | 121 |  |  |  | P.% sft |  | Rs. | 1059.355
3 | Cement plaster (1:4)upto 12 height 1/2" thick (GSI Item No.11 Page No. 52)
| In Side Tank | 2 | x ( | 10.25 | + | 10.25 | ) x | 11 | = | 451
| Out Side Tank | 2 | x ( | 11.5 | + | 11.5 | ) x | 11 | = | 506
| Top Beam | 2 | x ( | 11.5 | + | 10.25 | ) | 3 | = | 130.5
[8 empty] | Toatl | = | 1087.5
[7 empty] | Deduction |  | = |  | 81.5
[8 empty] | G.Total | = |  | 1006
| Qty | 1006 |  | Sft. | @ | RS. | 2283.93 |  |  |  | P.% Sq.ft |  | RS. | 22976.3358
4 | Making and fixing steel grated door complete with 1/16" thick sheeting including angle iron frame 2x2x3/8" and 3/4" Sq. yards 4" c/c with locking arrangement. (G.S. Item NO.24 Page No. 97)
|  | 1 | x | 3.5 | x | 6.5 |  |  | = | 22.75 |  | Sft.
| Qty | 22.75 |  | Sft. | @ | Rs. | 726.72 |  |  | P.Sq.ft |  |  | RS. | 16532.88
5 | Fabrication of heavy steel work with angle tear flat iron round iron and short iron for making trysses glydres tank etc. i.c cuting tanks etc i/c cutting drilling rewer ling in position(G.S.Item No. 2 Page no.91)
| Window | 2 | x | 3 | x | 3 |  |  | = | 18 | Sft.
|  | 18 | x | 4 |  |  |  | = | 0.64286 |  | Cwt.
112
| Qty | 0.64286 | Cwt. |  | @ | Rs. | 4928.49 |  |  | P.Cwt |  |  | RS. | 3154
6 | Supplying and fixing in position iron / steel grill of 3/4" x 1/4" size flat iron of approved design i/c painting 3 coat etc. complete ( Weight not be less then 3.7 lbs /sq. foot of finished grill) (G.S. Item No. 26 Page No. 93)
|  | 2 | x | 3 | x | 3 |  |  | = | 18 |  | Sft.
| Qty | 18 |  | S,ft | @ | Rs. | 180.5 |  |  | P.Sq.ft |  |  | RS. | 3249
7 | Dismantiling of cement concrete plain (1:3:6) (G.S.I No.19-B Page No. 10)
Around the P H plinth wall
|  | 2 | x ( | 23 | + | 18 | ) x | 0.75 | x | 2 | = | 123
|  | 1 | x ( | 23 | x | 18 | ) x | 0.33 |  |  | = | 136.62
[10 empty] | Total | = | 259.62
| PH. Deduction | 1 | x | 11.5 | x | 11.5 | x | 0.33 |  | (-) | = | 43.6425
[8 empty] | Total |  | = |  | 215.9775
| Qty | 215.9775 |  | Cft. | @ | Rs. | 1306.8 |  | P.% Cft. |  |  |  | RS. | 2822.394
8 | Cement concrete plain i/c placing compacting finishing and curing complete i/c screening & washing of stone aggregate w/o shuttering (G.S. Item No. 5 Page No. 15) Ratio (1:3:6)
Same quantity Item No. 7
| Qty | 215.98 |  | Cft. | @ | Rs. | 12595 |  |  | P.%cft |  |  | RS. | 27202.681
9 | Reinforced cement concrete work i/c all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid separately. This rate also i/c of forms moulds lifting shuttering curing rendering and finishing the exposed surfaces i/c screening and washing of stone aggregate (roof slabs beams columns rafts lintels and other structural member laid in situ or precast laid in position complete in all respect (G.S. Item No. 6 Page No. 16) 1:2:4
Same quantity Item No. 1
| Qty | 389 |  | cft. | @ | Rs. | 337 |  |  | P.Cft. |  |  | RS. | 131093
10 | Fabrication of Mild steel reinforcement for cement concrete including cutting bending laying in position, making joints & fastenings including cost of binding wire (also includes removal of rust from bars) (G.S.I.No.8 (b) P-16) (USING TAR BARS).
| 389 | x | 4.5 | [7 empty] | = | 15.6295 | cwt.
112
| Qty | 15.63 |  | cwt. | @ | Rs. | 5001.7 |  |  | P.cwt. |  |  | RS. | 78176.571
11 | Providing C.I Main hole cover M frame i/c Cost of material etc (P.H.S.I No. 1 Page No. 35)
| 2 | x | 1.75 | [7 empty] | = | 3.5 | Cwt.
| Qty | 3.5 |  | Cwt. | @ | Rs. | 6985 |  |  | P.Cwt. |  |  | RS. | 24447.5
12 | P/F in position C.C. foundation 1:3:6 M.S ladder of M.S angle iron 2" x 2" x 1/4" a part with M.S Bar 3/4 " dia space 1.00 apart painting 3 cost with anti corrosive steel paint etc. complate ( PHS Item No. 3 Page No. 55)
| Out Side | 1 | x | 50 | [6 empty] | = | 50 | Rft.
| In Side | 1 | x | 5 | [6 empty] | = | 5 | Rft.
[9 empty] | Total |  | = | 55 | Rft.
| Qty | 55 |  | Rft. | @ | Rs. | 799 |  |  | P.Rft. |  |  | RS. | 43945
13 | Cement plaster (1:4)upto 12 height 1/2" thick (GSI Item No.11 Page No. 52)
| I/S TankWall | 2 | x ( | 9.5 | + | 9.5 | ) x | 4 |  |  | = | 152 | S.ft
| Bed | 1 | x | 9.5 | x | 9.5 |  |  |  |  | = | 90.25 | S.ft
[8 empty] | Toatl |  |  | = | 242.25 | S.ft
| Qty | 242.25 |  | Sft. |  | @ | Rs. | 2283.93 |  | P% Sft. |  |  | RS. | 5532.8204
14 | Supply of dumpoo /pudlo fixed with cement Plaster etc. (PHSM Item No. 46)
|  | 1.77 | x | 3.5 | [6 empty] | = | 6.195 | Lbs
| Qty | 6 |  | Lbs | @ | Rs. | 52.82 |  | P.Lbs |  |  |  | RS. | 316.92
15 | Preparing surface and painting of door a window in any type etc. Door na dwindow only type (G.S. Item No. 5 d Page No. 68) (2 Coats)
| Door | 2 | x | 3.5 | x | 6.5 |  |  |  |  | = | 45.5
| Window | 2 | x | 2 | x | 3 | x | 3 |  |  | = | 36
[8 empty] | Toatl |  |  | = | 81.5
| Qty | 81.5 |  | Sft. | @ | Rs. | 2116.41 |  |  | P %.Sft |  | = | RS. | 1724.8741
16 | Providing Cement concrete Topping (G.S. Item No. 5 Page No. 18) Ratio (1:2:4)
| 1 | x | 10.33 |  | x | 10.33 |  |  |  |  | = | 106.7089
| Qty | 106.7089 |  | Sft. | @ | Rs. | 3275.5 |  |  | P.%Sft |  | = | RS. | 3495.25
17 | Laying white marble flooring fine dressed on the surface without winding set in line moter 1:2 including rubbing and polishing of the joints (G.S. Item No. 28 B Page No. 43) 3/4" Thick Flooring
| HSR Roof | 11.5 |  | x | 11.5 | [5 empty] | = | 132.25
| P H Roof | 11.5 |  | x | 11.5 | [5 empty] | = | 132.25
[8 empty] | ToTal |  |  | = | 264.5
| Qty | 264.5 |  | Sft. | @ | Rs. | 298.4 |  |  | P.Sft |  |  | RS. | 78926.8
18 | Providing Laying & Fixing in tranch i/c fitting jointing & testing P.E Pipe (PHS I No.F Page No. 25)
3" Dia
| Input pipe | 1 | x | 28 | = | 28 | rft.
| output pipe | 1 | x | 25 | = | 25 | rft.
| over floeing | 1 | x | 2 | = | 2 | rft.
|  | Total |  |  | = | 55
| Qty | 55 | rft. |  | @ | Rs. | 148 |  | P.rft. |  |  |  | RS. | 8140
19 | C.I Sluice Vqlve heavy pattern (Test Pressure 300 Ib /sq.inch
(Imported ) (PHSM.Item No. 2 page No. 12)
3" Dia
|  | 1 | x | 2 | = | 2 | Nos.
| Qty | 2 | Nos. |  | @ | Rs. | 4290 |  | Each |  |  |  | RS. | 8580
21 | Flanged adapter (N.S)
3" Dia
|  | 1 | x | 9 | = | 9 | Nos.
| Qty | 9 | Nos. |  | @ | Rs. | 675 |  | Each |  |  |  | RS. | 6075
22 | C.I Reflex Valveheavy pattern (Test pressure21.0 kg/sq or 300 lbs /sq. inch )(S.M.item No. 6/b : page No. 12)
3" Dia
|  | 1 | x | 1 | = | 1 | Nos.
| Qty | 1 | Nos. |  | @ | Rs. | 1543.75 |  | Each |  |  |  | RS. | 1543.75
23 | P.E Special for filling of meterial /Special Page No. 19-(2)D
Equal Tee 75 x 75 x75(3 x3 x3)
|  | 1 | x | 2 | = | 2 | Nos.
| Qty | 2 | Nos. |  | @ | Rs. | 1341 |  | Each |  |  |  | RS. | 2682
24 | Supplying P.E Band (S.M.I No-A Page No.18)
3" Dia
|  | 1 | x | 5 | = | 5
| Qty | 5 | No. |  | @ | Rs. | 1118 |  | Each |  |  |  | RS. | 5590
25 | C.I Band with Falnged ends with holes including turning and facing of flanged for all size (P.H.S.I No.11 Page No,12)
3" Dia
|  | 1 | x | 6.68 | = | 6.68 | Kg.
| Qty | 6.68 |  | Kg. | @ | Rs. | 120 |  | P.Kg |  |  |  | RS. | 801.6
26 | C.I Tapper flat bottom or centeral flanged ends with holes including turning and facing of flanged for all size(P.H.S.I No.9 Page 11)
| 3" X 2" | = | 1 | x | 5.25 |  | = | 5.25 | kg.
| 3" X 2 1/2" | = | 1 | x | 5.25 |  | = | 5.25 | kg.
|  |  |  | Total |  | Total | = | 10.5 | kg.
| Qty | 10.5 |  | Kg | @ | Rs. | 120 |  | P.Kg |  |  |  | RS. | 1260
27 | Jointing C.I /M.S flanged pipes and specials flanged and inside a trinch including supplying rubber packing of the require thickness nuts , bolts,with washers etc and other tools required for jointing and testing the joint to the specified pressure etc complete .(P.H.S Item No.1 Page No.40)
3 " Dia
|  | 1 | x | 8 | = | 8 | Joint
| Qty | 8 | Joint |  | @ | Rs. | 499 |  | P.Joint |  |  |  | RS. | 3992
28 | Priming coats of chalk distumper (G.S.Item No.23 Page No.53 )
(2 Coats)
| P.H Roof | 1 | x | 10.25 | x | 10.25 |  |  |  |  | = | 105.0625
| Walls in side | 2 | x ( | 10.25 | + | 10.25 | ) x | 10 |  |  | = | 410
[10 empty] | Total | = | 515.0625
| Qty | 515.0625 |  | S.ft | @ | Rs. | 442.75 |  | P%Sft. |  |  |  | RS. | 2280.4392
Distemper(GSI NO )
| Qty | 515.0625 |  | S.ft | @ | Rs. | 1043.75 |  | P%Sft. |  |  |  | RS. | 5375
29 | Prepairing the surface and painting with weather Coat i/e Rubbering the surface with rubbing bricks etc complete( S.I No. 38 (AB) Page No.55)
| Pump House out Side |  |  | 2 | x | (11.50+11.50)x10.0 |  |  |  | = |  | 460
|  |  |  | 2 | x | (11.50+11.50)x4.0 |  |  |  | = |  | 184
[10 empty] | Total |  | 644
| Qty | 644 |  | Sft. | @ | Rs. | 1948.1 |  | P% Sft. |  |  |  | RS. | 12545.764
30 | Painting new surface (Item No. 5© Page No. 68)
(3 Coats)
| Door | 2 | x | 3.5 | x | 6.5 |  |  |  |  | = | 45.5 | S.ft
| Window | 2 | x | 2 | x | 3 | x | 3 |  |  | = | 36 | S.ft
[10 empty] | Total | = | 81.5 | S.ft.
| Qty | 81.5 |  | Sft. | @ | Rs. | 2116.41 |  | P%sft. |  |  |  | RS. | 1724.8741
31 | Water Reducing admixture A.R-163 rate of 0.30 liter per one bag of cement (Rate Approved)
|  | 68.46 |  | x | 0.3 |  | = | 20.538 | Ltr
| Qty | 20.53 |  | Ltr | @ | Rs. | 195 |  | P.Ltr |  |  |  | RS. | 4003.35
[12 empty] | TOTAL | RS. | 530431/-
31 | Carriage of meterial 0f 100 cft. 5 tons of all meterial like stone aggregate spwall cool lime etc B.G fail festering paint and crossing bridge guarder pipe sheets rails M.S Bar etc. or 1000 nos bricks 10" x 5" x 3" or 1000 Nos. 12"x6"x2" or 150 Cft.of trucks of any other means owned by the contractor (CS Item No. 1 Page No. 1) (all lead approved)
bajri from crusher to site of work (Lead upto 29 milles)
| Qty | 541 |  | cft. | @ | Rs. | 1520.84 |  | P %cft |  |  |  | RS. | 8227.7444
Hill sand from ghaghar to site of work (Lead upto 43 milles)
| Qty | 320 |  | cft | @ | Rs. | 1976.68 |  | P %cft |  |  |  | RS. | 6325.376
Cement from Jawedan Cement Factory to site of work (Lead upto 34 milles)
| Qty | 107 |  | bags | @ | Rs. | 26.73 |  | P/Bag |  |  |  | RS. | 2860.11
Steel from Pakistan steel to site of work (Lead upto 39 milles)
| Qty | 15.63 |  | cwt | @ | Rs. | 18.46 |  | P. cwt |  |  |  | RS. | 288.5298
Differa nce of Meterial
Cement
|  |  |  | 107 |  | Bag | x | 180 |  | P.Bag |  |  | Rs. | 19260
Steel
|  |  |  | 15.63 |  | Cwt. | x | 1200 |  | P.Cwt. |  |  | Rs. | 18756
P.E Pipe from Pipe Factory (Lead upto 34 Miles)
[6 empty] | 55 | Rft. | x | 53.02 |  | P.%Rft. |  | Rs. | 29.161
CEMENT
|  |  |  | 107 |  | Bag | X | 180 |  | P.BG |  |  | RS. | 289
[11 empty] | G.Total | Rs. | 605438
| Asistant Engineer | [9 empty] | EXECUTIVE ENGINEER
| PUBLIC HEALTH ENGINEERING(O&M) | [9 empty] | PUBLIC HEALTH ENGINEERING(O&M)
| SUB-DIVISION SHAH MUREED | [9 empty] | DIVISION KARACHI